Local Action Plan (LAP)

Lead partner for pilot (PP3): RRA Zeleni kras – RDA Green Karst

Pilot location: Mt Snežnik (Slovenia)

Draft version: v0.1 (for internal review)

Pivka, 3.10.2025

Vsebina

6.1. Contextual Introduction	3

6.2. Overview of the Local Action Plan	4

6.3. Common methodology followed for the design of the Local Action Plan	4

Phase 1 – Preparation & Planning	5

Phase 2 – Data collection & analysis	5

Phase 3 – Awareness & co‑design	5

Phase 4 – Action planning, equality & monitoring	5

6.4. Local Action Plan Synthesis Table	7

6.5. LAP Actions Worksheets	8

PP3_01	8

Monitoring and micro-habitat restoration for rare plants (Spremljanje stanja populacij redkih vrst)	8

PP3_02	10

Famous Plants of Snežnik (Znamenite rastline Snežnika)	10

PP3_03	12

Guided excursions & lecture (Strokovne ekskurzije in predavanja)	12

PP3_04	14

Visitor impact monitoring & carrying capacity (Sviščaki educational trail & Snežnik summit)	14

PP3_05	16

Support for establishment of Regional Park Snežnik (Vzpostavitev Regijskega parka Snežnik – podpora)	16

PP3_06	18

Sviščaki learning trail refurbishment (Obnova učne poti Sviščaki)	18

6.6 Appendices	19

6.1. Contextual Introduction

Provide a concise description of the pilot area, including its geographical, cultural, and socio-economic characteristics, as well as its relevance to PROMONT’s objectives. Provide illustrative material to better present the pilot area (maps, photographs, etc.). The PROMONT project focuses on ADRION rural mountainous areas with unique biodiversity threatened by overexploitation, unsustainable economic activities, and seasonal mass tourism. Its main objective is to protect and regenerate fragile ecosystems by promoting environmental protection and regeneration actions involving and empowering local communities and stakeholders. Mention the biodiversity elements present in the pilot area and the pressures they face, along with opportunities for sustainable economic development that respect and enhance local ecosystems. [max 500 words]

Mt Snežnik (1,796 m) is the highest Slovenian mountain outside the Alps, forming a climatic and ecological bridge between the Mediterranean and continental Europe. The area is predominantly carbonate (high karst), with limited surface water and extensive forest cover transitioning to subalpine grasslands, rocky screes, and dwarf-pine (Pinus mugo) belts above the treeline. The Snežnik–Ždrocle forest reserve (≈794 ha; UNESCO “Ancient and Primeval Beech Forests of the Carpathians and Other Regions of Europe” core area ≈720 ha) holds unique upper montane and subalpine beech forests shaped by strong winds, long-lasting snow cover, and harsh temperatures. These beech stands exhibit distinctive, stunted “sabre” forms uncommon in the Alps, where the upper forest line is dominated by larch and spruce.

The mountain and the wider Snežnik–Javorniki complex fall within Natura 2000 (SI5000002 Snežnik–Pivka and associated sites), conserving multiple habitat types and species, including large carnivores (brown bear, wolf, lynx) and specialist birds (e.g., white-backed and three-toed woodpeckers). Biodiversity significance extends to rare and endemic plants of the summit grasslands and screes—among them Seseli malyi, Nigritella miniata, Arabis scopoliana, and Cerastium dinaricum—whose small, disjunct populations are vulnerable to shrub encroachment and visitor pressure.

Snežnik receives an estimated 15,000 hikers annually via four marked trails (plus an illegal hunting path). Concentrated use at the summit (a World Heritage buffer) has accelerated erosion, while trespassing into the pathless southern reserve persists. With rising attention following UNESCO inscription, careful visitor management is needed to safeguard fragile habitats and maintain visitor experience quality. Local livelihoods benefit from nature-based recreation; however, unmanaged visitation can compromise conservation outcomes. PROMONT therefore supports evidence-based monitoring, targeted restoration, and sustainable visitor management, coupling scientific practice with community engagement, interpretation, and culture-led awareness.

This LAP translates the site’s ecological priorities and socio-economic realities into actionable measures for 2025–2027, focusing on: (i) species and habitat monitoring with permanent plots and plant–pollinator studies; (ii) regeneration of open grassland microhabitats through selective encroachment control; (iii) carrying-capacity analytics and impact monitoring along the Sviščaki learning trail and summit access routes; (iv) culture and education actions (illustrated flora, exhibitions, guided excursions, lectures); and (v) improvement of visitor infrastructure where compatible with protection regimes.

6.2. Overview of the Local Action Plan

This section provides a general overview of the Local Action Plan, outlining its purpose, scope, and strategic approach. It summarizes the key thematic areas addressed, the expected outcomes for the pilot area, and how the plan integrates environmental, socio-economic, and cultural dimensions. The overview serves as a bridge between the contextual framework and the detailed action descriptions, giving readers a clear understanding of the LAP’s overall direction before exploring specific measures. [max 300 words]

The LAP for Snežnik mountain prioritizes biodiversity regeneration and sustainable visitation within a strictly protected forest-reserve setting. It sets a concise portfolio of five integrated actions that combine science, monitoring technology, and culture-based awareness to reduce pressure on sensitive habitats while enhancing the quality of nature experiences. The actions are designed to be realistic within 2025–2027 and replicable across ADRION pilot sites.

Strategically, the LAP pursues three results: (1) robust baselines and adaptive monitoring for target plant taxa and key habitats; (2) improved habitat quality and ecological connectivity on priority summit/scree grasslands; and (3) data-informed visitor management (carrying capacity, wayfinding, interpretation) that channels interest toward eco-compatible activities and off-loads the most fragile spots. Community-facing components (art–science publication, exhibition, excursions, lectures) build local pride and equip guides and businesses with biodiversity-friendly skills. Implementation follows PROMONT’s common methodology, ensuring transnational comparability and shared learning.

6.3. Common methodology followed for the design of the Local Action Plan

In this section, clearly explain how the planned actions contribute to PROMONT’s objectives; protecting mountain ecosystems, empowering local communities, supporting the local economy, and strengthening the transnational network of mountain stakeholders. Outline the steps taken to prepare this Local Action Plan, ensuring alignment with PROMONT’s collaborative, science-based, and transnational approach. Describe stakeholder engagement at local, regional, and transnational levels, the biodiversity data collection process (e.g., drone-based cameras, GIS mapping), and the analysis of ecological and socio-economic needs. Highlight the role of stakeholder engagement and data sharing in ensuring alignment with the transnational methodology and maximizing replicability. Mention participatory workshops, good practice transfer from other areas, and the co-design of biodiversity protection and regeneration actions. [max 300 words]

This LAP applies PROMONT’s D1.1.1 Common Methodology (WP1/A1.1) across four sequential phases and links each Snežnik action to the relevant steps and tools, ensuring comparability and replication across pilots.

Phase 1 – Preparation & Planning

We defined the Snežnik problem statement and Mountain Landscape Restoration (MLR) objectives (habitat openness, rare-plant viability, pressure management) in line with the methodology’s Section 5.1.1 and scoped the assessment to summit grasslands, screes and the Sviščaki learning trail (5.1.4). A core team (PP3, Natural History Museum Rijeka, technology providers) was formed per 5.1.3; stakeholder mapping and engagement follow the template in 5.1.2 (municipality, SiDG, SFI, TIC, NGOs, guides). Assessment criteria and indicators (5.1.5) combine ecological status (target taxa, habitat structure), visitor pressure, and feasibility/costs.

Phase 2 – Data collection & analysis

Following 5.2, we combine digital mapping (Copernicus/EO layers, high‑resolution trampling indices) with knowledge mapping from field experts and stakeholder workshops. PP3_04 (visitor impact & carrying capacity) implements “restoration opportunities” and spatial analysis (5.2.1–5.2.2) to identify sensitive segments, thresholds and management options. Biodiversity baselines for PP3_01 adopt the common species data model (taxonomy, habitat, threats, protection, population status) to ensure indicator alignment across partners.

Phase 3 – Awareness & co‑design

Per Section 5.3, co‑designed measures and culture‑based awareness are embedded through PP3_02 (art–science publication & exhibition) and PP3_03 (guided excursions & lecture), with messages tied to Natura 2000/UNESCO values and visitor‑behavior change.

Phase 4 – Action planning, equality & monitoring

The LAP worksheets translate evidence into implementable actions with KPIs, risks and timelines (Section 6 of the methodology). Equality and non‑discrimination provisions (5.4) are applied in participation, access, and benefit‑sharing (e.g., open training for local guides; inclusive event scheduling). Monitoring loops feed annual adjustments to PP3_01–PP3_05 and report to WP2/indicators for transnational synthesis.

Cross‑reference of actions to methodology steps.

- PP3_01: species database & indicators (5.1.5), field baselines, knowledge mapping inputs (5.2.2).

- PP3_02–PP3_03: awareness/engagement (5.3), inclusive participation (5.4).

- PP3_04: spatial analysis, carrying‑capacity modelling (5.2.1–5.2.2), management thresholds.

- PP3_05: option selection using criteria (5.1.5) and evidence from PP3_04 for low‑impact works.

6.4. Local Action Plan Synthesis Table

| Action Code | Action Title | Objective | Responsible Organization(s) |
| --- | --- | --- | --- |
| PP3_01 | Monitoring and micro-habitat restoration for rare plants / Spremljanje stanja redkih vrst | Establish baselines and stabilize/increase populations of Seseli malyi, Nigritella miniata, Arabis scopoliana, Cerastium dinaricum; improve habitat quality via selective encroachment control; document plant–pollinator networks. | RDA Green Karst (coord.), Natural History Museum Rijeka; experts (dr. Boštjan Surina). |
| PP3_02 | Famous Plants of Snežnik – art–science publication & exhibition / Znamenite rastline Snežnika | Publish 35 watercolour plates + essays; stage exhibition and guided programming; strengthen Natura 2000 awareness and nature-positive visitation. | RDA Green Karst (coord.), Natural History Museum Rijeka; experts (dr. Boštjan Surina). |
| PP3_03 | Guided excursions & public lecture / Strokovne ekskurzije in predavanja | Izvedba 2 celodnevnih ekskurzij v vrhu vegetacijske sezone na Snežniku Priprava in izvedba predavanja o botaničnih raziskavah na Snežniku, posebnosti in varstveni problematiki snežniške flore | RDA Green Karst (coord.), Natural History Museum Rijeka; experts (dr. Boštjan Surina). |
| PP3_04 | Visitor impact monitoring & carrying capacity – Sviščaki & summit / Monitoring učna pot Sviščaki in nosilna zmogljivost | Deliver two peak-season excursions and one lecture on Snežnik botany and conservation; equip local interpreters/guides with content. | RDA Green Karst (Arctur; municipality. |
| PP3_05 | Support for establishment of Regional Park Snežnik / Vzpostavitev Regijskega parka Snežnik (podpora) | Provide technical evidence, facilitation and alignment to support the Municipality of Ilirska Bistrica in the process to establish a Regional Park Snežnik, integrating conservation and community development. | Municipality of Ilirska Bistrica (lead – policy/act), RDA Green Karst (technical support), partners. |
| PP3_06 | Sviščaki learning trail refurbishment / Obnova učne poti Sviščaki | Light-touch upgrades (wayfinding, erosion control, interpretation) consistent with protection regimes. | SiDG (implementation) with RDA Green Karst (coord.). |

6.5. LAP Actions Worksheets

Provide detailed information for each action using the structure below.

| Action | PP3_01 |
| --- | --- |
|  | Monitoring and micro-habitat restoration for rare plants (Spremljanje stanja populacij redkih vrst) |
|  | Conduct population status assessments and habitat typology for Seseli malyi and Nigritella miniata (summit/scree micro-sites), with additional plant–pollinator monitoring for Arabis scopoliana and Cerastium dinaricum using compact 4K field cameras. Establish permanent plots; run pollen-flow trials (fluorescent dust) to quantify pollination pathways and reproductive success. Where justified, apply small-scale selective removal of Pinus mugo to maintain openness of priority grasslands. Produce standardized protocols and datasets to inform adaptive management and replication. |
| Objective(s) | - By 2027, complete baselines and 2-year trend data for 4 target species - Document plant–pollinator networks with ≥200 camera-hours and ≥6 pollen-flow trials; publish a monitoring protocol usable across PROMONT pilots. - Prepare a micro-habitat restoration recommendation (incl. selective dwarf-pine removal where appropriate) and obtain competent-authority feedback. |
| Background information | Summit grasslands and screes host small, disjunct populations of Red List-relevant plants threatened by shrub encroachment and concentrated visitation. Previous records confirm rarity and vulnerability; on-site implementation has lacked standardized, site-level monitoring and pollination data. The action fills this gap and integrates restoration with visitor management. |
| Associated Attribute | Subalpine grasslands and screes near the summit; flagship rare plants linking Natura 2000 and UNESCO beech-forest values. |
| Priority | High priority |
| Responsible Staff | Dejan Iskra , Morana Polovič, dr. Boštjan Surina |
| Involved Actors | RDA Green Karst |
| Cost | 8.500,00 EUR |
| Funding possibilities | PROMONT budget |
| Time schedule | 2026 - 2027 |
| Key Performance Indicators | - ≥4 taxa monitored annually; - ≥12 permanent plots; - ≥200 camera-hours; - ≥6 pollen-flow trials; - ≥10% habitat-quality improvement on treated micro-patches; protocol delivered (Y/N). KPIs to be confirmed with external expert |
| Risk Management | Environmental: disturbance during flowering—mitigate via timing, minimal-impact methods, and seasonal access notes. Socio-economic: limited volunteer uptake—mitigate via targeted outreach/training. Operational: adverse weather/access—build buffer days; equipment redundancy. Financial: co-fund small gear via sponsors. |
| Current Status | Planning: species list, locations and methods defined; equipment shortlist prepared; local expert team identified. Public call to be issued in folowing week. |

| Action | PP3_02 |
| --- | --- |
|  | Famous Plants of Snežnik (Znamenite rastline Snežnika) |
|  | Produce a high-quality art–science publication featuring 35 A3 watercolour plates (Mihaela Prižmić) with concise essays (dr. Boštjan Surina) covering identification, ecology, threats, and cultural links; include an introductory chapter on the history of botanical research on Snežnik and an evaluation of its natural heritage. Launch a travelling exhibition aligned with the book release, accompanied by guided walks, a public lecture, and training for guides/interpretation providers. The project ties into the 200th anniversary (2027) of the first documented botanical ascent of Snežnik. |
| Objective(s) | Raise Natura 2000, PROMONT and nature protection awareness; equip guides with accurate content; shift interest from sensitive micro-sites toward knowledge-based experiences; deliver bilingual materials (SL/EN; optional HR) for regional reach. |
| Background information | Snežnik’s summit grasslands and screes host a concentration of rare and endemic plants at the north‑western edge of Dinaric ranges. Several taxa proposed for the book are nationally unique or at distribution margins (e.g., Carex kitaibeliana, Festuca bosniaca, Seseli malyi, Cerastium dinaricum, Arabis scopoliana, Nigritella miniata). Their small, disjunct populations and sensitive micro‑habitats coincide with popular hiking routes and a UNESCO beech‑forest buffer. Awareness among visitors and some local stakeholders is uneven; detailed, place‑based interpretation is scarce on site. An illustrated, peer‑reviewed art–science publication and exhibition can translate specialist knowledge into accessible messages, strengthen local pride, and redirect attention from the most fragile micro‑sites toward respectful, knowledge‑led experiences. It also provides a durable content base for guides, schools and visitor centres, complementing PP3_01 monitoring results. |
| Associated Attribute | Botanical heritage and rare/endemic flora of Snežnik; cultural identity and local pride. |
| Priority | HIgh |
| Responsible Staff | Project officers RDA Green Karst |
| Involved Actors | RDA Green Karst; museums/galleries; tourism board; printers; municipalities. |
| Cost | 23.000,00 EUR |
| Funding possibilities | PROMONT (pilota activities); municipal culture funds; Natura 2000 awareness grants; sponsors for printing/framing; ticketing/donation at exhibitions. |
| Time schedule | 2025–2027 (manuscript & artwork 2025–2026; editing/production Q1–Q2/2027; |
| Key Performance Indicators | - 1 publication (≥35 plates, ≥35 essays); - 1 travelling exhibition (≥3 venues); - ≥50 event participants; - ≥80% positive feedback; - ≥ 5 local guides trained with the content pack. |
| Risk Management | Production delays—use staged milestones; budget pressure—seek sponsors; scientific review bottlenecks—pre-plan peer review. |
| Current Status | Concept and preliminary species list ready; partners identified; |

| Action | PP3_03 |
| --- | --- |
|  | Guided excursions & lecture (Strokovne ekskurzije in predavanja) |
|  | Organize two full-day peak-season excursions (late June/early July; routes Grčovec–Sviščaki or reverse) and deliver one public lecture on Snežnik botany, uniqueness, and conservation issues. Include a short module for local guides/businesses on biodiversity-friendly practices and interpretation. |
| Objective(s) | Improve visitor behavior and diversify offers; train local interpreters; collect feedback for adaptive management. |
| Background information | With ≈15,000 ascents per year concentrated on a few approaches, the summit area and nearby learning trail experience seasonal crowding and localized erosion. At the same time, the reserve’s protection regimes (forest reserve rules, UNESCO buffer) are not widely understood by visitors. Local guides and businesses have limited access to up-to-date biodiversity content linked to rare-plant conservation and visitor etiquette. Guided excursions during peak flowering and a public lecture curated with scientific partners can deliver accurate messages, demonstrate good practice in situ (e.g., stay-on-trail, micro-site sensitivity), and collect feedback to refine management. These activities also build a constituency for PP3_06 (Regional Park process) by fostering informed, constructive dialogue. |
| Associated Attribute | Sustainable nature-based tourism and community capacity. |
| Priority | Medium |
| Responsible Staff | RDA Green Karst project officer; scientific lecturer. |
| Involved Actors | Natural History Museum Rijeka; local guides; tourism board; municipalities. |
| Cost | 700,00 EUR |
| Funding possibilities | PROMONT pilot project activities |
| Time schedule | 2026 |
| Key Performance Indicators | - ≥2 excursions/year; - ≥1 lecture/year; - ≥80% participant satisfaction; |
| Risk Management | Weather cancellations—define alternates; low uptake—coordinate with tourism board; ensure group-size caps to protect habitats.Mitigation: Capacity-building with universities/NGOs, citizen science initiatives. |
| Current Status | Routes and content outlined; partners confirmed in principle. |

| Action | PP3_04 |
| --- | --- |
|  | Visitor impact monitoring & carrying capacity (Sviščaki educational trail & Snežnik summit) |
|  | Install IR people-counters on the Sviščaki educational trail and key approaches to the summit to build a continuous visitation series. Compute satellite-based vegetation health and trampling metrics (3 m–50 cm resolution where available) and model environmental carrying capacity for sensitive segments. Integrate results into practical measures: seasonal caps, route adjustments, interpretive prompts, and wayfinding. |
| Objective(s) | Quantify visitor flows; detect off-trail pressure; set threshold-based management responses; shorten recovery times of trampled vegetation. |
| Background information | Visitor pressure has been identified as a primary risk for the Snežnik–Ždrocle reserve, particularly at the summit and along popular approaches. Current counts are partial and seasonal; off-trail movements are difficult to detect. Evidence from other mountain destinations shows that combining IR counters with satellite-derived vegetation-health and trampling indicators enables managers to quantify impact, identify hotspots, and set threshold-based responses. Carrying-capacity indices linked to observed recovery times help time closures, reroute flows, or apply light infrastructure where strictly necessary. Establishing this evidence base is prerequisite to any trail refurbishment (PP3_06) and provides transparent inputs for public discussions on future governance (PP3_05). |
| Associated Attribute | Visitor use patterns interacting with sensitive subalpine grasslands and UNESCO beech-forest values. |
| Priority | High |
| Responsible Staff | RDA Green Karst (coord.) |
| Involved Actors | Murmuration (EO analytics); Arctur (sensors/data); municipality; protected-area authorities. |
| Cost | 11.000,00 EUR |
| Funding possibilities | PROMONT pilot lines; municipal co-funding |
| Time schedule | 2025-2026 |
| Key Performance Indicators | - continuous daily counts at ≥2 points; c - carrying-capacity index published for ≥2 trail segments; |
| Risk Management | Data gaps from cloud cover—mix sensors/periods; device vandalism—protective casings; stakeholder acceptance—co-design measures with guides and authorities. |
| Current Status | Technical proposal defined; sites for counters under selection; data-sharing protocol in draft. |

| Action | PP3_05 |
| --- | --- |
|  | Support for establishment of Regional Park Snežnik (Vzpostavitev Regijskega parka Snežnik – podpora) |
|  | In line with the Municipality of Ilirska Bistrica’s public initiative to protect the wider Snežnik area as a Regional Park, this action provides PROMONT-based technical support and facilitation: (i) compile and deliver ecological and visitor‑pressure evidence (from PP3_01 and PP3_04) for park delineation and zoning; (ii) assist the municipality with participatory engagement (workshops, information materials, targeted meetings) to co‑create a park concept that links existing protections with sustainable development; (iii) contribute to the draft management concept (vision, objectives, compatible uses) and to the preparation of a draft legal act (outline and evidence annexes) led by the municipality; and (iv) promote cross‑border learning from comparable regional parks. The legal establishment process and final decision rest fully with the Municipality and competent authorities; PROMONT’s role is supportive and non‑regulatory. |
| Objective(s) | Align conservation and community development in the Snežnik area; support a transparent, inclusive designation process; ensure evidence‑based boundaries and management guidelines consistent with Natura 2000 and local needs. |
| Background information | The Municipality of Ilirska Bistrica has announced an initiative to establish Regional Park Snežnik to conserve a largely uninhabited, predominantly forested high‑karst landscape while supporting community development. Public information stresses that edge villages are not intended to be inside the park footprint and that the concept will be co‑created with residents and experts. Given rising visitation following UNESCO recognition and Natura 2000 obligations, a coherent regional‑park framework can align conservation rules, visitor management, and local opportunities. PROMONT can contribute only supporting tasks—evidence synthesis, facilitation and communication—while the legal process, drafting and adoption remain with the Municipality and competent authorities. |
| Associated Attribute | Policy/management framework for the wider Snežnik landscape. |
| Priority | High (policy-enabling). |
| Responsible Staff | Municipality project officer (lead); RDA Green Karst pilot coordinator (support). |
| Involved Actors | Municipality of Ilirska Bistrica; residents and village councils; SiDG; tourism board (TIC); NGOs; expert institutions (museums, universities); protected-area authorities. |
| Cost | N/A |
| Funding possibilities | Municipal budget; national nature-conservation/territorial management funds; other programmes for participatory planning. |
| Time schedule | 2025–2027: information & dialogue (2025–2026); draft concept and delineation (2026); draft act and consultations (2026); decision by competent bodies (timeline per municipal process). |
| Key Performance Indicators | - Act of Regional park Snežnik confirmed |
| Risk Management | Divergent stakeholder expectations—mitigate via transparent process and clear benefits; legal/administrative delays—build realistic milestones; misinformation—use official channels and trusted intermediaries. |
| Current Status | Municipal initiative announced; stakeholder dialogue and evidence preparation ongoing. PROMONT alignment established through PP3_01, PP3_02–PP3_04. |

| Action | PP3_06 |
| --- | --- |
|  | Sviščaki learning trail refurbishment (Obnova učne poti Sviščaki) |
|  | Light-touch upgrades to the Sviščaki learning trail to protect sensitive spots and improve visitor guidance: repair and stabilize eroded segments; renew/relocate waymarks and interpretive points; add minimal infrastructure (e.g., step stones, low barriers) where needed; ensure all works comply with forest-reserve restrictions and Natura 2000 guidelines. |
| Objective(s) | Reduce micro-site erosion and trampling; improve visitor flow and safety; direct attention to eco-compatible viewpoints and content. |
| Background information | The Sviščaki learning trail is a gateway to Snežnik and could provide alternative means for visiting Snežnik mountain. Localized erosion, shortcutting and wayfinding gaps are reported at several segments, and interpretive content is outdated in places. Because the area lies within or adjacent to sensitive habitats and strict protection, any works must be minimal, reversible and timed outside breeding/flowering periods. Analytics from PP3_04 will pinpoint priority hotspots and inform design choices (e.g., signage relocation, micro-barriers, step stones). Refurbishment therefore focuses on guiding behaviour and protecting micro-sites rather than expanding facilities, and must be coordinated with competent authorities. |
| Associated Attribute | Visitor infrastructure intersecting sensitive habitats. |
| Priority | Medium |
| Responsible Staff | Position within the organization and the contact of the person being responsible for the achievement and implementation of this objective. (telephone, email or address) |
| Involved Actors | SiDG (implementer); RDA Green Karst (coordination & compliance). |
| Cost | N/A (aproximatelly 50.000,00 EUR) |
| Funding possibilities | SiDG funding under PUN project (cohesion funds) |
| Time schedule | 2026 - 2027 |
| Key Performance Indicators | - Updated trail |
| Risk Management | Permitting delays—early coordination; budget constraints—phase works; environmental risk—seasonal timing and method statements to avoid disturbance. |
| Current Status | SiDG is finalising project proposal together with other local stakeholders |

6.6 Appendices

Attach all relevant supporting materials that provide additional context or evidence for the Local Action Plan. These may include:

- Maps and spatial data: Geographic boundaries, protected areas, eco-itinerary routes, biodiversity hotspots.

- Technical reports and studies: Baseline biodiversity assessments, socio-economic analyses, feasibility studies.

- Stakeholder documentation: Lists of involved actors, signed agreements, workshop minutes, consultation records.

- Visual materials: Photographs, infographics, promotional material.

- Regulatory references: National/regional policies, conservation plans, planning permissions.

- Monitoring tools: Indicator sheets, data collection templates, survey questionnaires.

- Other relevant material and documentation.

Ensure that each appendix is clearly referenced in the main text and labelled for easy navigation by readers.

A curated list of 35 candidate taxa for plates and essays (to be finalized during manuscript development), including: Edraianthus graminifolius, Carex kitaibeliana, Festuca bosniaca, Seseli malyi, Trinia carniolica, Scabiosa silenifolia, Arabis scopoliana, Cerastium dinaricum, Campanula waldsteiniana, Campanula justiniana, Aquilegia kitaibeliana, Ranunculus traunfellneri, Nigritella miniata, Saxifraga moschata, Saxifraga sedoides, Carex rupestris, Achillea clavenae, Heliosperma alpestre, Ranunculus hybridus, Pulsatilla alpina subsp. austroalpina, Arabis vochinensis, Valeriana elongata, Omalotheca supina, Cypripedium calceolus, Chouardia litardierei, Leontopodium alpinum (var. krasense), Asperula beckiana, Gentianella liburnica, Athamanta liburnica, Lomelosia graminifolia, Salvia officinalis, Peltaria alliacea, and reserves under consideration (e.g., Astragalus liburnicus, Hyssopus officinalis, Ruscus hypoglossum, Oxytropis neglecta).

(The final selection and texts will ensure compliance with protection regimes for any sensitive-location data.)